## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## ProductBacklog
Product Backlog - Project Title
User Stroy | Story Point(s) | Priority
As a user, I should be able to start the main page and continue the survey. | 2 | 5 | Medium | High | Low
As a user , I can take a part in the survey. | 4 | 5 | 3 | 5 | 1
As a user, I can select best option for the questions. | 2 | 1
As a user, I can see the my survey result. | 3 | 3
As a user, I can see my result comparing with participants choice. | 4 | 3
As a Participants, I can able to start the main page. | 3 | 5
As a Participants, I am able to modify questions and the given option. | 2 | 5
As a Participants , I can add, edit the question. | 3 | 5
As a Participants ,I am able to delete the question and the option. | 4 | 5
As a Participants ,I am able to retive the questions from the database. | 4 | 3
As a Participants, I am able to check the users questions. | 3 | 3
As a Participants , I am able to tally the questions and user's answers. | 3 | 3
As a user, I am able to choose freely given options from the survey. | 2 | 1
As a user, I am able to delete my own survey. | 2 | 3
As a Participants, I am able to delete and add users. | 2 | 3

## sprint_backlog_sprint1 (2)
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task : Make a question on rough paper | 2 | Oluwole | Finished | 2 | 1 | 2 | 1 | 1
Task : Made home page | 2 | Shiva | Finished | 2 | 1 | 4 | 3 | 1
Task : Copy the question on mysql table | 4 | Shantosh | Finished | 2 | 2 | 1 | 2 | 2
Task: Linked questioner page to the home page | 2 | Shiva | Finished | 2 | 2 | 1 | 2 | 2
User Story #2
Task : made sample of project | 4 | Shiva | Finished | 2 | 1 | 1 | 2 | 1
Task: divided task as interest | 2 | Shantosh | Finished | 2 | 1 | 1 | 2 | 1
Task: Plan how to start the project | 4 | Oluwole | Finished | 2 | 1 | 2 | 1 | 1
Task: collecting the ideas to the project. | 2 | Bawan | Finished | 1 | 1 | 1 | 2 | 2
User Story #3
Task: made required questions for the survey. | 2 | Shantosh | Finished | 2 | 3 | 2 | 3 | 2
Task: made formate for the output of survey. | 2 | Bawan | Finished | 3 | 4 | 3 | 2 | 3
Task: made sql tabl format. | 2 | Oluwole | Finished | 2 | 2 | 3 | 2 | 3
Task : insert the required data to mysql database. | 2 | Shiva | Finished | 2 | 2 | 1 | 2 | 3
User Story #4
Task : made dao connection file for main part | 4 | Shiva | Finished | 2 | 2 | 3 | 2 | 4
Task : select some related images for the project | 2 | Shantosh | Finished | 1 | 1 | 1 | 2 | 2
Task : collect data from different sources. | 4 | Bawan | Finished | 2 | 1 | 3 | 4 | 4
Task : Place selected images in right place | 4 | Oluwole | Finished | 1 | 1 | 2 | 1 | 1
User Story #5
Task: made show participants jsp file | 2 | Oluwole | Finished | 2 | 1 | 2 | 4 | 3
Task: made delete java file | 4 | Shantosh | Finished | 4 | 2 | 2 | 2 | 3
Task: made Qdao file for questions | 4 | Shiva | Finished | 2 | 1 | 2 | 2 | 3
Task: made insert java file | 2 | Bawan | Finished | 2 | 3 | 2 | 2 | 4
TOTAL |  |  |  | 40 | 33 | 39 | 43 | 46
From this sprint we learn how to do task in group and how to communicate with each other, how to devide the task accroding to the interest and knoledge.

## sprint_planning_meetings
Spring Planning | Participants
Week 12 | Shiva | Shantosh | Oluwole | Bawan
Online | Online | Online | Online | Online | If physically present mark X
2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-03-25
Week 14 | Shiva | Shantosh | Oluwole | Bawan
Online | Online | Online | Online | Online
2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-04-06
Week 14 | Shiva | Shantosh | Oluwole | Bawan
Online | Online | Online | Online | Online
2020-04-09 | 2020-04-09 | 2020-04-09 | 2020-04-09 | 2020-04-09
Week 15 | Shiva | Shantosh | Oluwole | Bawan
Online | Online | Online | Online | Online
2020-04-12 | 2020-04-12 | 2020-04-12 | 2020-04-12 | 2020-04-12
Week 15 | Shiva | Shantosh | Oluwole | Bawan
Online | Online | Online | Online | Online
2020-04-17 | 2020-04-17 | 2020-04-17
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## sprint2
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task : Made a Qdelete file for delete questions. | 2 | Bawan | Finished | 2 | 3 | 4 | 4 | 3
Task : Made a showquestions jsp file for show questions. | 2 | Oluwole | Finished | 2 | 2 | 4 | 3 | 2
Task : Newquestion jsp file for questiosns | 4 | Shantosh | Finished | 2 | 2 | 4 | 2 | 4
Task: Made index.jsp file and insertdata java file | 2 | Shiva | Finished | 2 | 4 | 3 | 4 | 3
User Story #2
Task: made showquestions.java file | 2 | Oluwole | Finished | 3 | 2 | 1 | 2 | 1
Task: made showquestion.jsp file | 2 | Bawan | Finished | 2 | 2 | 2 | 1 | 3
Task: made mysql file for database | 2 | Shiva | Finished | 2 | 1 | 2 | 2 | 3
Task: made start.jsp file | 2 | Shantosh | Finished | 2 | 2 | 1 | 3 | 2
User Story #3
Task: Made showparticipants.java file | 4 | shiva | Finished | 3 | 4 | 4 | 4 | 4
Task : make showparticipants .jsp file | 4 | Shiva | Finished | 2 | 4 | 3 | 4 | 4
Task: made newquestion.jsp file for questions | 4 | shantosh | Finished | 2 | 2 | 2 | 3 | 2
Task: make update.java file for participants | 4 | Shantosh | Finished | 2 | 2 | 2 | 2 | 4
User Story #4
Task : made somehtml and style.css file | 4 | Shiva | Finished | 2 | 2 | 2 | 3 | 4
Task : make read to update file | 4 | Shantosh | Finished | 2 | 3 | 2 | 4 | 2
Task: join all made file in one project | 4 | Shantosh | Finished | 4 | 4 | 4 | 4 | 4
Task : join all made file in one project | 4 | Shiva | Finished | 4 | 4 | 4 | 4 | 4
User Story #5
Task : try to fix bugs after joining all files in one project | 2 | Shiva | Finished | 3 | 3 | 3 | 3 | 3
Task: Find bugs of the project | 2 | Shantosh | Finished | 3 | 3 | 3 | 3 | 3
Task: fixed shown errors | 2 | Shiva | Finished | 4 | 4 | 4 | 4 | 4
Task: fixed shown errors | 2 | Shantosh | Finished | 4 | 4 | 4 | 4 | 4
TOTAL |  |  |  | 52 | 57 | 58 | 63 | 63
In this sprint we devided diffrent task to diffrent person as his interest and after doing his task we joined all files and fixed the bugs and finished our given task. According to the guidelines we are able to finalized our project as plan and shedule.